## Summary Minutes-MeetingClie (2)
Capstone Project Title: Student Full name: Hariprasanth Sinnavajoumouny Internal Supervisor name: Dr, Sara Zandi External (client) Supervisor name: Dr, Louis Boapasem
Date and Week | Attendance Name | Capstone project GDDA7123C Summary of the meeting with client/ industry (external supervisor)
2024-04-16 | Dr, Sara Zandi, Dr Louis Boamponsem, Dr Mohammad Norouzifard and Hariprasanth | "* Project Introduction: Overview of the Particulate matter PM10 air and requirement of the project outcome. . * Expectation of project: A visualization dashboard is expected to created using the data from the client API which has PM10 info for Takapuna area * Discussion on data on the API connection : if there is a possibility of the data size is growing to be an big data then a cloud solution could be implemented. * Existing Tools: Discussed the current existing tool which could be a open source Sousing Jupyter notebook to do the w scraping of the data and do the EDA and Visualization and possible use of connecting to PowerBi of Tableau also discussed. * Data Sharing: Agreed to sign the confidentiality agreement with the Client ."
2024-06-13 | Dr, Sara Zandi, Dr Louis Boamponsem and Hariprasanth | * Dr, Louis approved with the project development direction as it is being done in Python(in Jupiter notebook) * Dr, Sara suggested to use an open Source GUI like TKinter for displaying the visualization performed in the Jupyter notebook and Dr louis approved the suggestion * How to Adress the missing values was discussed and Dr louis refered to fill it with mean values and even MISSforest ML algorithm an data manipulation algorithm has been used by Dr, Sara Zandi published article on AQI was suggested in my proposal was asked to try the suggest them the best method.

## External Meeting Minutes
Capstone Project Title: Student Full name: Internal Supervisor name: External (client) Supervisor name:
Date and Week | Attendance Name | Capstone project GDDA7123C Summery of the meeting with client/ industry (external supervisor)